## Product Backlog
Priority | Features | Implementation Tasks | Completion | Responsibility
1 | The MyDesign family of apps forms the basis for both the instruction and application of design through the use of simple icons, templates and interfaces.
2 | First implementation will be a web application optimized for the Chrome browser | decide on and set up configuration management system
3 |  | select technology to support front and back-end for alpha prototype development and demonstration
4 |  | define major product components (< 10) and overall responsibility for each
5 |  | define integration and test responsibility
6 | Users can register and log in as students, instructors, professionals and managers | log in screen with access controls
7 |  | simplified registration screen(s) for students
8 |  | simplified registration screen(s) for instructors
9 |  | simplified registration screen(s) for managers
10 |  | simplified registration for screen(s) professionals
11 | Users can register a new project or sign in to an existing project | project select screen with access controls
12 |  | simplified registration screen(s) for new project
13 | Users are guided to a design step consistent with the status of their project | screens defining design components and steps
14 |  | new project defaults to design step 1
15 |  | existing project defaults to design step consistent with current status
16 | A Dashboard screen for each design step shows status of design, collaborators, messages, mentors, portfolios, and resources relevant to the user registration and project | dashboard screen template
17 |  | home screen template
18 |  | apps screen(s) template
19 |  | sketches screen(s) template
20 |  | examples screen(s) template
21 |  | resources screen(s) template
22 |  | collaborators screen(s) template
23 |  | mentors screen(s) template
24 |  | progress screen(s) template
25 |  | message board screen(s) template
26 |  | rubric screen(s) template
27 |  | portfolios screen(s) template
28 |  | dashboard screen
29 | Populate design step 4 with relevant information, indexed by registration and project type | home screen
30 |  | apps screen(s)
31 |  | sketches screen(s)
32 |  | examples screen(s)
33 |  | resources screen(s)
46 |  | collaborators screen(s)
47 |  | mentors screen(s)
34 |  | progress screen(s)
35 |  | message board screen(s)
36 |  | rubric screen(s)
37 |  | portfolios screen(s)
38 | MyDesign links phones, tablets, and computers to support professionals in the office or field; or students of all ages, who can interact across platforms in virtual teams with teacher/mentor guidance and support. | instructor dashboard screen
39 |  | class select and assignment screens
40 |  | team select and assignment screens
41 |  | class progress screen(s)
42 |  | team progress screen(s)
43 |  | student progress screen(s)
44 |  | modify student dashboard screen
45 |  | instructor assessment screen
48 | MyDesign tags user activity and performance to form a record of design activities to establish a basis for comparing work and progressively awarding credit, thus creating a foundation to unify the reward for design across disciplines and communities.
49 | MyDesign records user activities across design disciplines and communities that can be reviewed and presented to advertisers, publishers, college admissions offices, competition organizers, employers and other stakeholders in the design process.

## Sprint #1 Backlog
Features | Implementation Tasks | Responsibility | Status
First implementation will be a web application optimized for the Chrome browser | decide on and set up configuration management system
select technology to support front and back-end for alpha prototype development and demonstration
define major product components (< 10) and overall responsibility for each
define integration and test responsibility
…select as many from the product backlog as you can get finished in the sprint
demonstrate sprint features